## Sheet1
Task | Start Date | End Date | Duration | Comments
Project Proposal | 2018-01-12 | 2018-01-15 | 3 | Done
C Code Prototype | 2018-01-12 | 2018-01-14 | 2 | Done
Basics of 8085 & Assembly Language | 2018-01-15 | 2018-05-01 | 106 | Adjust
Analysing Hardware Requirements | 2018-02-01 | 2018-02-08 | 7
Schematic Development | 2018-02-08 | 2018-02-15 | 7 | Adjust
Constructing the Board Layout | 2018-02-15 | 2018-02-21 | 6 | Midsems Near
SD(1):Basic Tic-Tac-Toe Model | 2018-03-10 | 2018-03-17 | 7 | After midsems
SD(2):Constructing the Minmax Algorithm Model | 2018-03-10 | 2018-03-30 | 20 | Concurrently
Ordering and Obtaining the PCB | 2018-03-10 | 2018-03-17 | 7
Board Fabrication | 2018-03-18 | 2018-03-20 | 2
Conducting Alpha Tests | 2018-03-20 | 2018-03-30 | 10 | Check